## Risk Register
Risk ID | Related Use‑Case | Risk Description | Root Cause | Impact | Likelihood | Priority | Risk Rating | Mitigation / Control | Risk Owner | Status
R‑05 | UC‑03 | Poor‑quality requirements generate invalid test cases | Users override validation warnings | Low test quality, rework effort | High | High | Critical | Mandatory warning visibility, risk flag, audit trail, QA review | QA Lead | Open
R‑10 | UC‑06 | Test cases are published without proper approval | Approval bypass or role misconfiguration | Audit failure, release risk | Low | High | Critical | Hard approval gate, role‑based enforcement | QA Lead | Open
R‑13 | UC‑08 | Regression impacts are missed after requirement changes | No systematic impact analysis | Defects escape to production | High | High | Critical | Automated change detection + regression recommendations | QA Lead | Open
R‑18 | NFR‑04 | Data leakage outside BCCH boundary | External GenAI exposure | Regulatory breach | Low | Critical | Critical | Internal‑only deployment, no external calls | IT Security | Closed
R‑01 | UC‑01 | Unauthorized users gain access to Test Genie | Weak access control rules or bypass of AD validation | Security breach, compliance violation | Medium | High | High | Enforce BCCH AD group validation + mandatory approval + audit logs | IT Security | Open
R‑03 | UC‑02 | Large requirement documents fail ingestion | File size or format limitations | Test creation delays | Medium | High | High | Define max file size (50 MB), graceful error handling | Product Owner | Open
R‑06 | UC‑03 | Requirement quality rules do not match BCCH standards | Rules hardcoded incorrectly | Governance non‑compliance | Low | High | High | Validate rules with QA Governance before MVP | QA Governance | Open
R‑08 | UC‑05 | Generated test cases do not follow BCCH test template | AI output inconsistency | Rejection during review, rework | Medium | High | High | Enforce structured output schema and validation guardrails | QA Governance | Open
R‑11 | UC‑06 | Changes to test cases are not traceable | No versioning or audit history | Compliance & audit gaps | Medium | High | High | Versioning, approval history, timestamped logs | Compliance | Open
R‑15 | NFR‑01 | Test generation exceeds acceptable SLA | Large documents or high load | User dissatisfaction, productivity loss | Medium | High | High | Performance tuning, async processing, SLA monitoring | Architecture | Open
R‑19 | NFR‑05 | Insufficient log retention violates compliance | Improper retention policy | Audit failure, penalties | Low | High | High | Enforce 7‑year retention as per BCCH policy | Compliance | Open
R‑02 | UC‑01 | Access approvals remain pending indefinitely | No approval expiry or escalation | Delayed onboarding, productivity loss | Medium | Medium | Medium | Auto‑expiry of requests after 7 days, email/escalation reminders | IT Security | Open
R‑04 | UC‑02 | Image‑only or scanned PDFs are not interpreted correctly | Limited OCR capability | Incomplete or incorrect test cases | Medium | Medium | Medium | Basic OCR in MVP; advanced OCR backlog | Product Owner | Open
R‑07 | UC‑04 | Missing business/application context reduces accuracy | Optional context not supplied by testers | Low‑quality test scenarios | Medium | Medium | Medium | UI nudges, recommended context templates | Product Owner | Open
R‑09 | UC‑05 | Language handling causes incorrect interpretation | Mixed or Chinese requirements | Functional coverage gaps | Medium | Medium | Medium | Language detection + controlled translation strategy | Product Owner | Open
R‑12 | UC‑07 | Publishing failures to Squash cause data inconsistency | Integration or manual upload issues | Misaligned test repositories | Medium | Medium | Medium | Publish confirmation, retry mechanism, user alerting | Tool Owner | Open
R‑14 | UC‑08 | Regression updates applied without human validation | Over‑automation | Incorrect regression suite | Low | Medium | Medium | Recommendation‑only updates with approval | QA Lead | Open
R‑16 | NFR‑02 | System cannot scale to peak concurrent usage | Under‑provisioned infrastructure | System slowdowns | Medium | Medium | Medium | Capacity planning, load testing | IT Architecture | Open
R‑17 | NFR‑03 | Source systems unavailable cause data loss | Weak error handling | Loss of user input | Low | Medium | Medium | Retry, draft autosave, graceful failure handling | Product Owner | Open
R‑20 | NFR‑06 | Adding new connectors requires code changes | Non‑plug‑in architecture | Higher cost, slower rollout | Medium | Medium | Medium | Connector‑based extensible design | Architecture | Open
R‑21 | NFR‑07 | Poor usability leads to low adoption | Lack of onboarding & guidance | Tool under‑utilization | Medium | Medium | Medium | In‑app walkthroughs and help | Product Owner | Open

## Clarafication questions
Use‑Case ID | Requirement Area | Question | Response (Example) | Stakeholder | Priority | Risk Impact | Status
UC‑01 | Access Management | Should access be restricted only to BCCH AD groups or also specific project roles? | BCCH AD group membership is mandatory; project role validation is Phase‑2. | IT Security | High | High | Open
UC‑01 | Access Management | Is Line Manager approval mandatory for all non‑AD users or only first‑time users? | Mandatory only for first‑time access requests. | IT Security | High | Medium | Open
UC‑02 | Requirement Ingestion | What is the maximum supported file size for Word/PDF uploads? | Up to 50 MB per document in MVP. | Test SMEs | High | Medium | Open
UC‑03 | Requirement Validation | Can users override quality warnings and proceed? | Yes, with visible risk warning and audit trail. | QA Lead | High | High | Open
UC‑03 | Requirement Validation | Should quality scores be persisted for audits? | Yes, store scores, gaps, overrides, and timestamps. | Compliance | High | High | Open
UC‑05 | Test Generation | Must generated tests follow BCCH test case template? | Yes, mandatory adherence to BCCH standard format. | QA Governance | High | High | Open
UC‑06 | HITL Review | Is QA Lead approval mandatory for every test case? | Required for critical / release‑impact tests only. | QA Lead | High | High | Open
UC‑06 | HITL Review | Should rejected test cases retain version history? | Yes, full versioning with approval comments. | Compliance | High | High | Open
UC‑07 | Publishing | Can test cases be published without QA Lead approval? | No, approval is a hard gate. | QA Governance | High | High | Open
UC‑08 | Regression Management | How should regression impact be determined? | Rule‑based detection first, AI suggestions later. | QA Lead | High | High | Open
NFR‑01 | Performance | Maximum acceptable test generation time for large inputs? | ≤ 3 minutes for up to 50‑page documents. | Architecture | High | High | Open
NFR‑03 | Reliability | Expected system behavior if source systems are unavailable? | Graceful error handling with retry; no data loss. | Product Owner | High | Medium | Open
NFR‑04 | Security | Is any data allowed to leave BCCH network boundaries? | No external data exposure permitted. | IT Security | High | Critical | Closed
NFR‑05 | Auditability | How long should artifacts and logs be retained? | Minimum 7 years as per BCCH retention policy. | Compliance | High | High | Open
UC‑02 | Requirement Ingestion | Are scanned, image‑only PDFs supported? | Partially via basic OCR; advanced OCR in backlog. | Product Owner | Low | Medium | Open
UC‑04 | Context Enrichment | Can context be reused across multiple requirements? | Yes, reusable within a project session. | Testers | Low | Low | Open
UC‑01 | Access Management | Should access requests auto‑expire if not approved within a time window? | Yes, auto‑expire after 7 days. | IT Security | Medium | Low | Open
UC‑02 | Requirement Ingestion | Can a single ingestion contain multiple requirements? | Yes, multiple requirements per document are supported in MVP. | QA Lead | Medium | Medium | Open
UC‑03 | Requirement Validation | Are BCCH quality rules configurable or hardcoded? | Hardcoded for MVP; configurable in Phase‑2. | QA Governance | Medium | Medium | Open
UC‑04 | Context Enrichment | Are business/application context fields mandatory? | Optional but strongly recommended. | Product Owner | Medium | Low | Open
UC‑05 | Test Generation | Should test case IDs be auto‑generated by the system? | Yes, internal IDs mapped on publish. | Tool Owner | Medium | Low | Open
UC‑05 | Language Support | Should test cases always be generated in English? | MVP: English output only; bilingual later. | Business | Medium | Medium | Open
UC‑07 | Publishing | Is direct API publishing to Squash required for MVP? | MVP supports UI‑based publish; API later. | Tool Owner | Medium | Medium | Open
UC‑08 | Regression Management | Should regression updates be auto‑applied? | No, only recommendations; user approval required. | QA Lead | Medium | Medium | Open
NFR‑02 | Scalability | Required number of concurrent users? | At least 100 concurrent users in MVP. | IT Architecture | Medium | Medium | Open
NFR‑06 | Extensibility | Should ingestion integrations follow plugin architecture? | Yes, connector‑based design mandated. | Architecture | Medium | Medium | Open
NFR‑07 | Usability | Is product onboarding / guided walkthrough required? | Yes, in‑product guidance required for MVP. | Business | Medium | Low | Open

## RTM_STRIDE
Req / Use‑Case ID | Requirement / Function | STRIDE Threat | Threat Description | Risk ID | Security Control / Mitigation | Control Type | Owner
UC‑01 | User Access via MyApps | Spoofing | Unauthorized user poses as valid tester | R‑01 | BCCH AD group validation + MFA | Preventive | IT Security
UC‑01 | Access Approval Workflow | Elevation of Privilege | User gains access without approval | R‑10 | Line‑manager approval + IT provisioning gate | Preventive | IT Security
UC‑01 | Access Logging | Repudiation | User denies requesting access | R‑11 | Audit logs with timestamp & approver | Detective | Compliance
UC‑02 | Requirement Ingestion | Tampering | Uploaded files altered or corrupted | R‑03 | Secure upload + checksum validation | Preventive | Architecture
UC‑02 | PDF/Word Ingestion | Information Disclosure | Sensitive data exposed during parsing | R‑18 | Internal‑only processing, no external calls | Preventive | IT Security
UC‑03 | Requirement Validation | Tampering | Poor‑quality requirement bypasses quality checks | R‑05 | Mandatory validation + override flag | Preventive | QA Governance
UC‑03 | Quality Score Storage | Repudiation | No evidence of ignored warnings | R‑11 | Persist scores, warnings & overrides | Detective | Compliance
UC‑05 | Test Case Generation | Spoofing | AI generates tests without valid requirement context | R‑08 | Traceability enforcement (Req → TC) | Preventive | QA Governance
UC‑05 | Test Case Generation | Information Disclosure | Requirement data leaks via AI model | R‑18 | Internal model, guardrails, no training on prod data | Preventive | IT Security
UC‑06 | HITL Review | Elevation of Privilege | Tester publishes without QA approval | R‑10 | Hard approval gate (QA Lead role) | Preventive | QA Lead
UC‑06 | Versioning | Repudiation | Changes made without accountability | R‑11 | Version history + approval comments | Detective | Compliance
UC‑07 | Publish to Squash | Tampering | Test cases modified during publish | R‑12 | Publish confirmation + checksum | Preventive | Tool Owner
UC‑08 | Regression Analysis | Denial of Service | Missed regression impacts overwhelm QA later | R‑13 | Automated change detection | Detective | QA Lead
UC‑08 | Regression Updates | Elevation of Privilege | System auto‑updates regression without approval | R‑14 | Recommendation‑only + approval required | Preventive | QA Lead
NFR‑01 | Performance | Denial of Service | Large inputs degrade system | R‑15 | SLA monitoring + async processing | Corrective | Architecture
NFR‑05 | Audit Logs | Repudiation | Logs unavailable for audit | R‑19 | 7‑year retention policy | Preventive | Compliance